## Example risk register
CONSTRUCTION RISK REGISTER EXAMPLE
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | LIKELY TIMING OF RISK | RISK TRIGGER | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER | OTHER NOTES
10001 | MM/DD/YY | Materials | If there are changes in architectural plans that require additional or different resources, then there will be delays. | 1 | 8 | 8 | The risk is present throughout the process of finalizing architectural plans. | There are changes in the architectural plans. | A designated team member will continually monitor any proposed changes in architectural plans and ensure communication between architectural and construction teams about proposed changes. | No current issues | Joe Smith; architectural liaison
10002 | MM/DD/YY | Contracts | If contractual issues among contractors, subcontractors, or vendors arise, then there will be delays or cost overruns. | 2 | 4 | 8 | The risk is present before most contract work commences. However, the risk will also be present when additional contracts are added in the early phases of construction. | The contracts manager reports any potential contract issues. | The contracts manager will continually monitor contracts, alert the team when there are issues, and ensure that the team addresses and resolves contract issues before they cause delays. | Working on one unresolved issue with the electrician's contract; meeting set for May 2nd | Sue Johnson, contracts manager
10003 | MM/DD/YY | Permits / Regulations | If obtaining appropriate construction permits takes longer than planned, then there will be delays. | 2 | 8 | 16 | The risk is present throughout the construction phase of the project, including when securing required permits at the beginning of construction. | Construction permits do not arrive within the required timeframe. | The construction manager, or another designated team member, will monitor the project schedule and deadlines and ensure that all permits can accommodate the project's construction schedule. | All deadlines currently being monitored | Dale Swenson, construction manager
10004 | MM/DD/YY | Construction Site | If unexpected hazardous waste is found on the property, it will require mitigation or cleanup. | 1 | 8 | 8 | The risk is present throughout the project, especially toward the beginning when conducting site preparation work. | On-site managers report an issue, especially during site preparation. | The construction manager will assign a team member to monitor and explore any possible issues with hazardous waste. | No issues found to this point | Jeff Baker, construction assistant
|  |  |  | 1 | 1 | 1
|  |  |  | 1 | 2 | 2
|  |  |  | 1 | 4 | 4
|  |  |  | 1 | 8 | 8
|  |  |  | 1 | 16 | 16
|  |  |  | 2 | 16 | 32
|  |  |  | 3 | 16 | 48
|  |  |  | 4 | 16 | 64
|  |  |  | 5 | 16 | 80

## BLANK - Risk Reg
PROJECT RISK REGISTER TEMPALTE
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | LIKELY TIMING OF RISK | RISK TRIGGER | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER | OTHER NOTES
100 | 2026-05-12 | Human error | Scope creep | 5 | 8 | 40 | Near the middle of the project | Over-enthusiastic stakeholders | Stick firmly to what is agreed upon in the contract, remind comissioners that any extra features added will require more time and payment. | No current issues | Project manager
101 | 2026-05-12 | Human error | Delays from quality control | 5 | 2 | 10 | Throughout the project | dyslexia/mistype | use autofills when necessary during coding and auto correct in documentation | We are having members of the team read through all written work before final upload | Web developers (Ethan)
102 | 2026-05-12 | Friction | Scheduling | 4 | 4 | 16 | Throughout the project | Delayed responses/feedback, Unpredicatable personal schedules | Scheduling issues are inevitable, to resolve any scheduling issues it's important to keep clear communication with the rest of the team in order to resolve problems as they come in. | Regular communication takes place in person, and within calls | Project manager
103 | 2026-05-12 | Human error | Branching in the REPO | 2 | 2 | 4 | Throughout the project | Multiple people pushing to the REPO | Coordenate times for editing the REPO and/or be prepared to merge branches | All issues currently resolved | Web developers
104 | 2026-05-12 | PTO | Key team members unable to complete key parts for unavoidable reasons | 2 | 16 | 32 | Throughout the project | Family emergencies, personal emergencies (such as medical) | This should be accommadated for at the beginning of the project by allowing extra time for key points, so that any impacts had will not be as fatal to the project | No current issues | Project manager
105 | 2026-05-12 | Contracts | Legal issues | 1 | 16 | 16 | End of the project | Non-compliance with with 2020 Privacy nz act | Ensure that a lawyer reads through the terms and conditions, and the privacy policies before publishing the website. | Not a current issue, but any changes to what data the site collects are checked to ensure that they are compatible with the privacy act | Legal team and project manager
106 | 2026-05-12 | Human error | Delays from stakeholders regarding feedback | 4 | 2 | 8 | A risk all throughout the project | Late stakeholder feedback on crucial features | Set deadlines for when feedback is needed, send follow up emails before the date feedback is required | No issues with late feeback as of current | Ethan
107 | 2026-05-12 | Contracts | Copyright | 5 | 2 | 10 | End of the project | Similarity issues with images and audio content, and/or forgetting to replace placeholder images | Instead of using placeholder images of objects (i.e, an image of a watch you found online) use images with text descriptions instead. If commissioning someone, ensure that in contract they are liable for any copyright issues that arise from the images they create. | No current issues | Project Manager and web developers
108 | 2026-05-12 | Hardware | Hardware issues | 2 | 2 | 4 | Throughout the project | Issues with incompatible operating systems, or the use of old equipment | ensure that the equipment used has been recently purchaced and checked for faults, and that the software is compatible with the hardware | As Apple OS is tempramental, for many things, especially Git related, a Windows PC has been used instead of an Apple Macbook. | Project manager (Kat)
109 | 2026-05-12 | Contracts | Budget | 4 | 16 | 64 | Mid-End project | More staff required or scope creep or missmangagement | check in with management as well as the team to make sure that everything is within the bounds of the contract | No current issues | Project manager
110 | 2026-05-13 | Domain specific risk | Publishing/Deployment failure | 3 | 8 | 24 | Near the end of the project | Faults with either the hosting platform, or with the files compatibility | attempt deployment on a private/unknown server before a final publish that will allow for errors to be fixed before the final publish | No current issues | Web developers

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
Enter Risk Category titles below to populate the Risk Register Dropdown Menu.
RISK CATEGORY
Software
Hardware
PTO
Friction
Human error
Contracts
Domain specific risk
Category Eight
Category Nine
Category Ten
PROBABILITY
IMPACT