Enter title of this project in cell B2.
Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet.
Continue navigating down column A to hear further instructions.
Enter Company Name in cell B4.
A legend is in cells I4 through AC4. The Legend label is in cell G4.
Enter the name of the Project Lead in cell B5. Enter the Project Start date in cell C6 or allow the sample formula to find the smallest date value from the Gantt Data table.
Project Start Date: label is in cell B6.
A Scrolling Increment is in cell C7.
Months for the dates in row 7 are displayed starting in cells I6 through cell BL6.
Do not modify these cells. They are auto updated based on the project start date in cell F6.
Cells I9 through BL9 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated.
Do not modify these cells.
A scrollbar is in cells I8 through BL8.
To jump forward or backward in the timeline, enter a value of 0 or higher in cell C7.
A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule. B9 through G9 contains schedule information. Cells I9 through BL9 contain the first letter of each day of the week for the date above that heading.
All project timeline charting is auto generated.
Enter Project information starting in cell B11 through cell G11.
Enter Milestone Description, select a Category, assign someone to the task, and enter the progress, start date, and number of days for the task to start charting.
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row.
To add more items, insert new rows above this one.
Changing this number will scroll the Gantt Chart view.
## About
ABOUT THIS GANTT CHART

Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. / • Add the day you started your project in the Start Date. / • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

0

## Light
PROJECT TITLE

Company name					Legend:		On track					Low risk					Med risk					High risk					Unassigned
Project lead
Project Start Date:	Err:509					April					May					June
Scrolling Increment:	1					21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15

Milestone description	Category	Assigned to	Progress	Start	Days		T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M

TITLE 1
Task 1	Goal	Name	25%	21/04/2026	3		2	2	2
Task 2	Milestone			26/04/2026	1					1
Task 3	Low Risk		50%	18/04/2026	10
Task 4	Milestone			11/05/2026	1					1
Task 5	Med Risk		10%	27/04/2026	6
TITLE 2
Task 1	High Risk		60%	27/04/2026	13
Task 2	On Track		50%	29/04/2026	9
Task 3	Low Risk		33%	4/05/2026	11
Task 4	Milestone			6/05/2026	1					1
Task 5				7/05/2026	24
TITLE 3
Task 1	On Track			6/05/2026	4
Task 2	Med Risk			9/05/2026	14
Task 3	On Track			24/05/2026	6
Task 4	Goal			28/05/2026	3					2	2	2
Task 5	Low Risk			27/04/2026	19
TITLE 4
Task 1				31/05/2026	15
Task 2				14/06/2026	5
Task 3	Milestone			26/07/2026	1
Task 4
Task 5

To add more data, Insert new rows ABOVE this one

## Dark
Gantt Chart

Company name – Goku Finance					Legend:		On track					Low risk					Med risk					High risk					Unassigned
Project lead
Project Start Date:	20/02/2026					March					April					May
Scrolling Increment:	30					22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16

Milestone description	Category	Assigned to	Progress	Start	Days		S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S

Iteration 1
Set up Git and GitHub	High Risk	Kat	100%	25/02/2026	1
Testing Repo Commits	Med Risk	All	100%	25/02/2026	3
Setting Up Communication	Med Risk	All	100%	4/03/2026	3
Creating personas	Med Risk	All	100%	10/03/2026	4
Reflection of Iteration 1	Low Risk	All	100%	18/03/2026	3
Iteration 2
Setting Up the Kanban	Low Risk	Kat	100%	25/03/2026	3
Gantt Chart	Low Risk	Tyler	100%	1/04/2026	2
Recourse List	Med Risk	Kat	33%	1/04/2026	3
Task 4	Milestone			3/04/2026	1					1
Progress Report	High Risk	Ethan		21/04/2026	24
TITLE 3
Task 1	On Track			12/03/2026	4
Task 2	Med Risk			15/03/2026	14
Task 3	On Track			30/03/2026	6
Task 4	Goal			25/04/2026	3					2	2	2
Task 5	Low Risk			18/03/2026	19
TITLE 4
Task 1				28/04/2026	15
Task 2				12/05/2026	5
Task 3	Milestone			23/06/2026	1
Task 4
Task 5

To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE

Company name					Legend:		On track					Low risk					Med risk					High risk					Unassigned
Project lead
Project Start Date:	Err:509					April					May					June
Scrolling Increment:	5					21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15

Milestone description	Category	Assigned to	Progress	Start	Days		T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M

TITLE 1
Task 1	Goal	Name	25%	21/04/2026	3		2	2	2
Task 2	Milestone			26/04/2026	1					1
Task 3	Low Risk		50%	18/04/2026	10
Task 4	Milestone			11/05/2026	1					1
Task 5	Med Risk		10%	27/04/2026	6
TITLE 2
Task 1	High Risk		60%	27/04/2026	13
Task 2	On Track		50%	29/04/2026	9
Task 3	Low Risk		33%	4/05/2026	11
Task 4	Milestone			6/05/2026	1					1
Task 5				7/05/2026	24
TITLE 3
Task 1	On Track			6/05/2026	4
Task 2	Med Risk			9/05/2026	14
Task 3	On Track			24/05/2026	6
Task 4	Goal			28/05/2026	3					2	2	2
Task 5	Low Risk			27/04/2026	19
TITLE 4
Task 1				31/05/2026	15
Task 2				14/06/2026	5
Task 3	Milestone			26/07/2026	1
Task 4
Task 5

To add more data, Insert new rows ABOVE this one